## Sheet1
Start Week | End Week | Description | Duration (Weeks)
1 | 4 | Implement a standard Boids algorithm that flocks a moving target | 4
5 | 10 | Extend the previous algorithm to have defensive maneuvers | 6
11 | 13 | Evaluate the two algorithms against each other | 3
14 | 17 | Majority development of report and finalisation | 4